## 任务列表-2021-08-30_10_26_59
里程碑 | 任务ID | 任务标题 | 任务创建者 | 任务类型 | 任务状态 | 逾期情况 | 标签 | 关联仓库 | 任务路径
openEuler-21.09-round-1 | I460IM | 【21.09】rsyslog服务启动失败 | ga_beng_cui | 缺陷 | 已完成 | 逾期 8 天完成 | sig/Base-service,block | src-openEuler/rsyslog | https://gitee.com/open_euler/dashboard?issue_id=I460IM
openEuler-21.09-round-1 | I462AA | [21.09arm/x86]使用pxe方式和半自动化方式进行安装虚拟机失败 | ga_beng_cui | 缺陷 | 已完成 | 逾期 8 天完成 | sig/sig-OS-Builder,block | src-openEuler/anaconda | https://gitee.com/open_euler/dashboard?issue_id=I462AA
openEuler-21.09-round-1 | I462HF | [21.09]systemd-localed服务启动失败 | ga_beng_cui | 缺陷 | 已完成 | 逾期 5 天完成 | sig/Base-service | src-openEuler/systemd | https://gitee.com/open_euler/dashboard?issue_id=I462HF
openEuler-21.09-round-1 | I468W9 | [openEuler-release] 安装ISO启动系统时执行/etc/profile.d/system-info.sh报错 | 机智的泡泡 | 缺陷 | 已完成 |  | sig/Base-service | src-openEuler/openEuler-release | https://gitee.com/open_euler/dashboard?issue_id=I468W9
openEuler-21.09-round-1 | I46AFQ | [NetworkManager] 安装openEuler 21.09系统后生成的DNS异常 | 机智的泡泡 | 缺陷 | 已取消 |  | sig/Networking | src-openEuler/NetworkManager | https://gitee.com/open_euler/dashboard?issue_id=I46AFQ
openEuler-21.09-round-1 | I46AHK | [systemd] 使用openEuler 21.09的virtual_machine_img起的vm缺失/etc/resolv.conf文件 | 机智的泡泡 | 缺陷 | 已完成 |  | sig/Networking | src-openEuler/systemd | https://gitee.com/open_euler/dashboard?issue_id=I46AHK
openEuler-21.09-round-1 | I46BOY | openEuler 21.09 rc1 x86_64 xfce图形界面打开firefox 提示firefox crash | 丈青山 | 缺陷 | 已完成 |  | sig/Application | src-openEuler/firefox | https://gitee.com/open_euler/dashboard?issue_id=I46BOY
openEuler-21.09-round-1 | I46DXG | aide --init 初始化数据库失败 | jinjin | 缺陷 | 已完成 |  | sig/Base-service | src-openEuler/aide | https://gitee.com/open_euler/dashboard?issue_id=I46DXG
openEuler-21.09-round-1 | I46F0D | 【安全加固指南】列举系统中全局的全局可写文件，语句排版错误 | jinjin | 缺陷 | 已完成 |  | sig/doc | openEuler/docs | https://gitee.com/open_euler/dashboard?issue_id=I46F0D
openEuler-21.09-round-1 | I46F0R | 存在全局可写文件，和安全加固指南描述不符 | jinjin | 缺陷 | 已取消 |  |  | src-openEuler/security-tool | https://gitee.com/open_euler/dashboard?issue_id=I46F0R
openEuler-21.09-round-1 | I46GOH | 【openEuler 21.09】【x86/arm】ltp执行用例min_free_kbytes时，用例卡住不动，系统提示out of memory | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel,block | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46GOH
openEuler-21.09-round-1 | I46HBG | 【21.09-RC1】安装kmod-kvdo存在warning信息 | 朱金龙 | 缺陷 | 已验收 | 完成 | sig/Runtime | src-openEuler/kmod-kvdo | https://gitee.com/open_euler/dashboard?issue_id=I46HBG
openEuler-21.09-round-1 | I46HN0 | 【21.09-RC1】首次安装storm报错，二次安装成功；卸载strom包，提示服务未找到 | 朱金龙 | 缺陷 | 已完成 | 逾期 2 天完成 | sig/sig-ai-bigdata | src-openEuler/storm | https://gitee.com/open_euler/dashboard?issue_id=I46HN0
openEuler-21.09-round-1 | I46HV8 | 【21.09-RC1】安装、卸载iavf软件包，有warn信息 | 朱金龙 | 缺陷 | 已验收 | 完成 | sig/Networking | src-openEuler/iavf | https://gitee.com/open_euler/dashboard?issue_id=I46HV8
openEuler-21.09-round-1 | I46IUJ | 【openEuler 21.09】【arm】ltp执行用例cpuset_memory_pressure_testset.sh时，导致系统重启 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel,block | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46IUJ
openEuler-21.09-round-1 | I46JH9 | eggo --version返回值不对 | haozi007 | 缺陷 | 已完成 |  | sig/sig-CloudNative | openEuler/eggo | https://gitee.com/open_euler/dashboard?issue_id=I46JH9
openEuler-21.09-round-1 | I46JI6 | 【21.09-RC1】digest-list-tools包的配置文件有问题，导致iavf、kmod-kvdo包安装有错误提示 | 朱金龙 | 缺陷 | 已完成 | 逾期 3 天完成 |  | src-openEuler/digest-list-tools | https://gitee.com/open_euler/dashboard?issue_id=I46JI6
openEuler-21.09-round-1 | I46K5N | 【21.09-RC1】storm软件包下的4个服务都启动失败 | 朱金龙 | 缺陷 | 已完成 | 逾期 2 天完成 | sig/sig-ai-bigdata | src-openEuler/storm | https://gitee.com/open_euler/dashboard?issue_id=I46K5N
openEuler-21.09-round-1 | I46K8O | openEuler 21.09版本qemu启动vfio设备失败 | Xinle.Guo | 缺陷 | 已完成 |  | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46K8O
openEuler-21.09-round-1 | I46KJH | 【21.09-0816】obs-server包下的obsscheduler和obsworker命令执行报错 | 郭晨阳 | 缺陷 | 已完成 | 完成 | sig/Others | src-openEuler/obs-server | https://gitee.com/open_euler/dashboard?issue_id=I46KJH
openEuler-21.09-round-1 | I46KNH | 【21.09-0816】libmemcached 包下的memcapable命令执行报错 | 郭晨阳 | 缺陷 | 已完成 | 完成 |  | src-openEuler/libmemcached | https://gitee.com/open_euler/dashboard?issue_id=I46KNH
openEuler-21.09-round-1 | I46KVF | 函数RunChainOfResponsibility的实现有问题，只执行了当前的Execute以及Next的Execute | wangfengtu | 缺陷 | 已完成 |  | sig/sig-CloudNative | openEuler/eggo | https://gitee.com/open_euler/dashboard?issue_id=I46KVF
openEuler-21.09-round-1 | I46M7C | 【21.09-RC1】卸载libcareplus软件包时有warning信息 | 朱金龙 | 缺陷 | 已完成 | 逾期 1 天完成 | sig/Virt | src-openEuler/libcareplus | https://gitee.com/open_euler/dashboard?issue_id=I46M7C
openEuler-21.09-round-1 | I46MJ9 | 【21.09】arm物理机出现内核报错Kunpeng920 not support 0 length | ga_beng_cui | 缺陷 | 已完成 | 逾期 2 天完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46MJ9
openEuler-21.09-round-1 | I46MJP | 【21.09】arm物理机出现内核报错Cmdq IO error, opcode = 8408, return = 2 | ga_beng_cui | 缺陷 | 已完成 | 逾期 2 天完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46MJP
openEuler-21.09-round-1 | I46NSS | 【21.09】【arm/x86】nfs远程挂载失败，报错：mount.nfs: mount system call failed | Emily_LiuLiu | 缺陷 | 已完成 | 逾期 2 天完成 | sig/Storage,block | src-openEuler/nfs-utils | https://gitee.com/open_euler/dashboard?issue_id=I46NSS
openEuler-21.09-round-1 | I46QWL | 【openEuler 21.09】【arm】ltp执行proc01用例失败。 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46QWL
openEuler-21.09-round-1 | I46QYL | 【openEuler 21.09】【arm】ltp执行memcg_failcnt用例失败。 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46QYL
openEuler-21.09-round-1 | I46R4M | 【openEuler 21.09】【arm/x86】ltp执行memcg_limit_in_bytes用例失败。 | 马增刚 | 缺陷 | 已完成 | 逾期 2 天完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46R4M
openEuler-21.09-round-1 | I46RI8 | 【openEuler 21.09】【arm/x86】ltp执行memcg_memsw_limit_in_bytes用例失败。 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46RI8
openEuler-21.09-round-1 | I46RLP | 【openEuler 21.09】【arm/x86】ltp执行memcg_use_hierarchy用例失败。 | 马增刚 | 缺陷 | 已完成 | 逾期 3 天完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46RLP
openEuler-21.09-round-1 | I46RNT | 【openEuler 21.09】【arm/x86】ltp执行tpci用例失败。 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46RNT
openEuler-21.09-round-1 | I46RRI | 【openEuler 21.09】【arm/x86】ltp执行cpuset_memory_spread用例，概率性失败。 | 马增刚 | 缺陷 | 已完成 | 逾期 3 天完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I46RRI
openEuler-21.09-round-1 | I46UE9 | 21.09版本net镜像iso kernel版本不正确，导致安装失败 | 张鹭 | 缺陷 | 已验收 | 完成 | sig/Runtime,block | src-openEuler/kmod-kvdo | https://gitee.com/open_euler/dashboard?issue_id=I46UE9
openEuler-21.09-round-1 | I46UJG | 创建nftables规则并备份json格式文件，在arm上，备份内容错误，在x86执行报错 | 王珊 | 缺陷 | 已完成 | 完成 | sig/Networking | src-openEuler/nftables | https://gitee.com/open_euler/dashboard?issue_id=I46UJG
openEuler-21.09-round-1 | I46UNY | [rust] rustdoc --target命令执行失败时信息描述错误 | 机智的泡泡 | 缺陷 | 已完成 |  | sig/sig-Rust | src-openEuler/rust | https://gitee.com/open_euler/dashboard?issue_id=I46UNY
openEuler-21.09-round-1 | I46VXD | [21.09]安装最小化，message日志出现关于selinux报错 | ga_beng_cui | 缺陷 | 已完成 | 逾期 1 天完成 | block | src-openEuler/selinux-policy | https://gitee.com/open_euler/dashboard?issue_id=I46VXD
openEuler-21.09-round-1 | I46W9U | 【21.09】arm物理机journalctl日志报错：No directory /sys/devices/platform/HISI0173:00 / | ga_beng_cui | 缺陷 | 已完成 | 完成 | sig/Computing | src-openEuler/irqbalance | https://gitee.com/open_euler/dashboard?issue_id=I46W9U
openEuler-21.09-round-1 | I46XXL | 处理错误格式的json，未提示错误 | 王珊 | 缺陷 | 已完成 | 完成 | sig/Base-service | src-openEuler/jq | https://gitee.com/open_euler/dashboard?issue_id=I46XXL
openEuler-21.09-round-1 | I46XZF | 配置firewalld记录被reject的数据包 | jinjin | 缺陷 | 已取消 |  | sig/Networking | src-openEuler/firewalld | https://gitee.com/open_euler/dashboard?issue_id=I46XZF
openEuler-21.09-round-1 | I46YK0 | [20.19][x86\arm]systemctl 查看服务状态显示的样式奇怪 | 黄蓉 | 缺陷 | 已完成 | 完成 | sig/Base-service | src-openEuler/systemd | https://gitee.com/open_euler/dashboard?issue_id=I46YK0
openEuler-21.09-round-1 | I46ZQ1 | [pkgship] 修改配置文件中redis_port异常时，启动服务报错，没有对应的提示 | 机智的泡泡 | 缺陷 | 已完成 |  | sig/sig-EasyLife | openEuler/pkgship | https://gitee.com/open_euler/dashboard?issue_id=I46ZQ1
openEuler-21.09-round-1 | I46ZZL | 【21.09】【arm/x86】garbd服务启动失败 | 黄蓉 | 缺陷 | 已完成 | 完成 | sig/Others | src-openEuler/galera | https://gitee.com/open_euler/dashboard?issue_id=I46ZZL
openEuler-21.09-round-1 | I4708E | 【21.09】【arm/x86】dovecot服务启动报错Error in configuration file /etc/dovecot/conf.d/10-ssl.conf | 黄蓉 | 缺陷 | 已取消 | 完成 | sig/Application | src-openEuler/dovecot | https://gitee.com/open_euler/dashboard?issue_id=I4708E
openEuler-21.09-round-1 | I471H5 | [pkgship] 在docker容器里安装pkgship的过程中报错，且ES无法启动 | 机智的泡泡 | 缺陷 | 已取消 |  | sig/sig-EasyLife | openEuler/pkgship | https://gitee.com/open_euler/dashboard?issue_id=I471H5
openEuler-21.09-round-1 | I4722F | 【openEuler 21.09】【arm/x86】mount绑定samba服务失败 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Networking | src-openEuler/samba | https://gitee.com/open_euler/dashboard?issue_id=I4722F
openEuler-21.09-round-1 | I472M0 | 【21.09】【arm/x86】fcoe服务启动失败 | 黄蓉 | 缺陷 | 已完成 | 完成 | sig/System-tool | src-openEuler/fcoe-utils | https://gitee.com/open_euler/dashboard?issue_id=I472M0
openEuler-21.09-round-1 | I472WA | 【21.09】【arm/x86】ldirectord服务启动后有错误Failed to parse PID from file /run/ldirectord.ldirectord.pid | 黄蓉 | 缺陷 | 已完成 | 完成 | sig/Others | src-openEuler/resource-agents | https://gitee.com/open_euler/dashboard?issue_id=I472WA
openEuler-21.09-round-1 | I473HW | 【openEuler 21.09】【arm/x86】ltp执行madvise09用例失败 | 马增刚 | 缺陷 | 已完成 | 完成 | sig/Kernel | openEuler/kernel | https://gitee.com/open_euler/dashboard?issue_id=I473HW
openEuler-21.09-round-1 | I4762C | 【fuzz】heap-buffer-overflow | jinjin | 缺陷 | 已完成 |  | sig/Others | src-openEuler/sleuthkit | https://gitee.com/open_euler/dashboard?issue_id=I4762C
openEuler-21.09-round-1 | I476B8 | 【fuzz】detected memory leaks | jinjin | 缺陷 | 已完成 |  | sig/Others | src-openEuler/sleuthkit | https://gitee.com/open_euler/dashboard?issue_id=I476B8
openEuler-21.09-round-1 | I47B4K | [21.09][x86/arm]auto_install_pkgship_requires.sh提示信息错误 | 黄蓉 | 缺陷 | 已完成 | 完成 | sig/sig-EasyLife | src-openEuler/pkgship | https://gitee.com/open_euler/dashboard?issue_id=I47B4K
openEuler-21.09-round-1 | I47C7N | [21.09][Wallaby][glance] 文件属组不对，导致服务无法启动 | huangtianhua | 缺陷 | 已完成 |  | sig/sig-openstack | openEuler/openstack | https://gitee.com/open_euler/dashboard?issue_id=I47C7N
openEuler-21.09-round-1 | I47GOF | [21.09][Wallaby][placement] api httpd服务入口启动失败 | 刘胜 | 缺陷 | 已完成 |  | sig/sig-openstack | openEuler/openstack | https://gitee.com/open_euler/dashboard?issue_id=I47GOF