## openEuler 22.09版本缺陷总览
序号 | 里程碑 | 任务ID | 任务标题 | 任务状态
1 | openEuler 22.09 | I5LMXU | [22.09 Yoga] openstack heat相关软件包安装失败 | 已完成
2 | openEuler 22.09 | I5M6FK | 【22.09】智能运维Aops，启动gala-gopher服务时，ksliprobe探针启动失败 | 已完成
3 | openEuler 22.09 | I5M6NZ | 【22.09】智能运维Aops,gala-inference服务文件的description描述有误 | 已完成
4 | openEuler 22.09 | I5M6OI | 【22.09】智能运维Aops，gala-anteater提供服务文件，但是启动方式有误 | 已完成
5 | openEuler 22.09 | I5MD4N | 【22.09】智能运维Aops，gala-anteater命令行启动失败 | 已完成
6 | openEuler_embedded-22.09-round-1 | I5MSFH | 【22.09 RC1】【arm/x86】nfs-blkmap服务停止状态failed | 已挂起
7 | openEuler_embedded-22.09-round-1 | I5OEIE | 【2209-r1】使用sdk编译libcap失败 | 待办的
8 | openEuler_embedded-22.09-round-1 | I5OLP0 | openEuler的arm32 SDK source时出错 | 待办的
9 | openEuler-22.09-Alpha | I5J302 | 【安装冲突arm/x86_64】openEuler:22.09分支fwupd与dbxtool包安装冲突 | 已完成
10 | openEuler-22.09-Alpha | I5J312 | 【安装冲突arm/x86_64】openEuler:22.09分支libtraceevent与perf包安装冲突 | 已取消
11 | openEuler-22.09-Alpha | I5J36Q | 【安装冲突 arm/x86_64】python3-wrapt在22.09分支存在安装冲突 | 已完成
12 | openEuler-22.09-Alpha | I5J3K1 | 【安装冲突arm/x86_64】openEuler:22.09分支mariadb与mysql包安装冲突 | 已完成
13 | openEuler-22.09-Alpha | I5J3LC | 【安装冲突arm】openEuler:22.09分支xorg-x11-server与libxcvt包安装冲突 | 已完成
14 | openEuler-22.09-Alpha | I5J3NM | 【安装冲突arm/x86_64】openEuler:22.09分支postgresql与libpq包安装冲突 | 待办的
15 | openEuler-22.09-Alpha | I5J3V2 | 【安装冲突arm/x86_64】openEuler:22.09分支openmpi-devel与pmix-devel包安装冲突 | 已完成
16 | openEuler-22.09-Alpha | I5J3VQ | 【arm/x86_64】22.09分支安裝bind和bind-pkcs11有异常告警 | 已完成
17 | openEuler-22.09-Alpha | I5J3WP | 【arm/x86_64】openEuler:22.09分支custom_build_tool-nodebug安装有warning信息 | 已完成
18 | openEuler-22.09-Alpha | I5J3XI | 【安装冲突aarch64/x86_64】openEuler:22.09分支python3-augeas与pkgship包安装冲突 | 已完成
19 | openEuler-22.09-Alpha | I5J3ZS | 【安装冲突arm/x86_64】openEuler:22.09分支mysql5与greatsql包安装冲突 | 已完成
20 | openEuler-22.09-Alpha | I5J41G | 【安装冲突arm/x86_64】openEuler:22.09分支mysql-devel与mysql5-devel、mysql-help与mysql5-devel包安装冲突 | 已完成
21 | openEuler-22.09-Alpha | I5J46R | 【安装冲突x86_64】openEuler:22.09分支mariadb与greatsql安装冲突 | 已完成
22 | openEuler-22.09-Alpha | I5J476 | 【安装冲突arm/x86_64】openEuler:22.09分支jakarta-servlet与glassfish-servlet-api安装冲突 | 已完成
23 | openEuler-22.09-Alpha | I5J5D6 | 【arm/x86_64】22.09分支安裝卸载libcareplus-selinux有无用信息打印 | 已完成
24 | openEuler-22.09-Alpha | I5J5G3 | 【x86_64】22.09分支安裝linux-sgx-driver有异常告警 | 已完成
25 | openEuler-22.09-Alpha | I5J5HI | 【arm/x86_64】22.09分支安裝texlive-t2有异常信息 | 已完成
26 | openEuler-22.09-Alpha | I5J5JG | 【arm/x86_64】22.09分支安裝和卸载custodia有异常信息 | 已完成
27 | openEuler-22.09-Alpha | I5J7NF | 22.09分支安裝python3-horizon缺依赖 | 已完成
28 | openEuler-22.09-Alpha | I5J7Y7 | 【x86_64/aarch64】python3-muranoclient在22.09分支安装缺依赖python3.10dist(prettytable) < 0.8 | 已完成
29 | openEuler-22.09-Alpha | I5J806 | 【x86_64/aarch64】python3-neutron-tempest-plugin在22.09分支安装缺依赖python3.10dist(nose) >= 1.3.7 | 已完成
30 | openEuler-22.09-Alpha | I5J82J | 【x86_64/aarch64】python3-os-xenapi-tests在22.09分支安装缺依赖python3-os-xenapi = 0.3.4-1 | 已完成
31 | openEuler-22.09-Alpha | I5J844 | 【x86_64/aarch64】python3-pip-api在22.09分支安装缺依赖python3.10dist(pip) | 已完成
32 | openEuler-22.09-Alpha | I5J856 | 【x86_64/aarch64】python3-requirementslib在22.09分支安装缺依赖 | 已完成
33 | openEuler-22.09-Alpha | I5J86L | 【x86_64/aarch64】python3-senlinclient在22.09分支安装缺依赖python3.10dist(prettytable) < 0.8 | 已完成
34 | openEuler-22.09-Alpha | I5J87C | 【x86_64/aarch64】python3-trove-tempest-plugin在22.09分支安装缺依赖python3.10dist(psycopg2-binary) >= 2.6.2 | 已完成
35 | openEuler-22.09-Alpha | I5J8GS | 【22.09-ax86】验证全量卸载过程中，卸载NetworkManager-bluetooth时卸载了NetworkManager，导致虚拟机无法ssh连接 | 已完成
36 | openEuler-22.09-Alpha | I5J8WD | 【安装失败arm/x86_64】deepin-movie-devel安装失败 | 已取消
37 | openEuler-22.09-Alpha | I5J9L7 | 22.09分支安裝ovirt-hosted-engine-setup时报冲突与ansible | 已取消
38 | openEuler-22.09-Alpha | I5JA2A | 【安装冲突arm/x86_64】openEuler:22.09分支 ansible与ansible-2.9包安装冲突 | 已完成
39 | openEuler-22.09-Alpha | I5JA77 | 【安装冲突arm/x86_64】openEuler:22.09分支 python3-suds-community与python3-suds2包安装冲突 | 已完成
40 | openEuler-22.09-Alpha | I5JAHZ | 【安装冲突x86_64】openEuler:22.09分支dtkcore-devel与dtkcore2-devel包安装冲突 | 已完成
41 | openEuler-22.09-Alpha | I5JAKI | 【安装冲突x86_64】openEuler:22.09分支python3-rtslib与python3-rtslib-fb包安装冲突 | 已完成
42 | openEuler-22.09-Alpha | I5JAMO | 【安装冲突x86_64】openEuler:22.09分支python3-migrate与python3-sqlalchemy-migrate包安装冲突 | 已完成
43 | openEuler-22.09-Alpha | I5JB33 | 【安装冲突arm/x86】22.09分支安装 dtkwidget-devel和dtkwidget2冲突 | 已完成
44 | openEuler-22.09-Alpha | I5JB6Y | 【22.09-arm/x86】使用2209_epol源安装中出现大量告警 | 已完成
45 | openEuler-22.09-Alpha | I5JBFZ | 【22.09-aarch64/x86_64】使用2209_epol源安装trafficserver包，出现告警信息 | 已完成
46 | openEuler-22.09-Alpha | I5JG1Y | 【安装冲突aarch64/x86_64】openEuler:22.09分支javamail与jakarta-mail包安装冲突 | 已完成
47 | openEuler-22.09-Alpha | I5JM2K | 【自编译失败】【x86】22.09环境，opa-psm2自编译失败 | 已完成
48 | openEuler-22.09-Alpha | I5JM71 | 【自编译失败】【x86】22.09环境，pytorch自编译失败 | 待办的
49 | openEuler-22.09-Alpha | I5JM97 | 【自编译失败】【x86】22.09环境，xorg-x11-drv-intel自编译失败 | 已完成
50 | openEuler-22.09-Alpha | I5JQK6 | 【22.09】rubygem-pg包本地自编译失败 | 已完成
51 | openEuler-22.09-Alpha | I5KREG | Xorg-x11-server启动失败 | 已完成
52 | openEuler-22.09-AT | I5I9YV | [22.09]安装界面字体样式与openEuler历史版本不同 | 已验收
53 | openEuler-22.09-AT | I5IDKW | [22.09]bind包卸载失败 | 已验收
54 | openEuler-22.09-AT | I5IDNK | [22.09]bind-chroot包卸载有报错信息 | 已验收
55 | openEuler-22.09-AT | I5IDTR | [22.09]bind-pkcs11包安装有报错信息，卸载失败 | 已验收
56 | openEuler-22.09-AT | I5IDXJ | [22.09]tracker3-miners包安装卸载有报错信息 | 已验收
57 | openEuler-22.09-AT | I5IE2B | [22.09]evolution-data-server包安装有报错信息 | 已验收
58 | openEuler-22.09-AT | I5IFOM | [22.09]targetcli命令执行报错 | 已取消
59 | openEuler-22.09-beta | I1TRZX | 【20.09-beta】【arm/x86】colm -m zhu mu.txt命令执行报错，C++导出代码失败 | 已挂起
60 | openEuler-22.09-beta | I5KMK3 | perl-Sys-Syslog build problem in openEuler:22.09 | 已完成
61 | openEuler-22.09-beta | I5KMK6 | scsi-target-utils build problem in openEuler:22.09 | 已完成
62 | openEuler-22.09-beta | I5KMKC | byte-buddy build problem in openEuler:22.09 | 已完成
63 | openEuler-22.09-beta | I5KMKS | libfprint build problem in openEuler:22.09 | 待办的
64 | openEuler-22.09-beta | I5KMKX | libnice build problem in openEuler:22.09 | 已完成
65 | openEuler-22.09-beta | I5KMKZ | mailman build problem in openEuler:22.09 | 已完成
66 | openEuler-22.09-beta | I5KML4 | activemq build problem in openEuler:22.09:Epol | 已完成
67 | openEuler-22.09-beta | I5KML9 | neo4j build problem in openEuler:22.09:Epol | 已取消
68 | openEuler-22.09-beta | I5KTDB | libmicrohttpd build problem in openEuler:22.09 | 已完成
69 | openEuler-22.09-beta | I5KTXG | openstack-cinder is unresolvable in openEuler:22.09:Epol | 已完成
70 | openEuler-22.09-beta | I5KTXK | python-rbd-iscsi-client is unresolvable in openEuler:22.09:Epol | 已完成
71 | openEuler-22.09-beta | I5KTXS | python-trio is unresolvable in openEuler:22.09:Epol | 已完成
72 | openEuler-22.09-beta | I5L362 | ansible is unresolvable in openEuler:22.09 | 已完成
73 | openEuler-22.09-beta | I5L3P9 | LZMA-SDK build problem in openEuler:22.09 | 已取消
74 | openEuler-22.09-beta | I5L3PC | imageTailor build problem in openEuler:22.09 | 已取消
75 | openEuler-22.09-beta | I5L3PD | install-scripts build problem in openEuler:22.09 | 已取消
76 | openEuler-22.09-beta | I5L3PF | mtd-utils build problem in openEuler:22.09 | 已取消
77 | openEuler-22.09-beta | I5L3PH | net-snmp build problem in openEuler:22.09 | 已完成
78 | openEuler-22.09-beta | I5L3PI | python-atomicwrites build problem in openEuler:22.09 | 已完成
79 | openEuler-22.09-beta | I5L3PJ | python-breathe build problem in openEuler:22.09 | 已完成
80 | openEuler-22.09-beta | I5L3PK | python-cppy build problem in openEuler:22.09 | 已完成
81 | openEuler-22.09-beta | I5L3PN | python-httmock build problem in openEuler:22.09 | 已完成
82 | openEuler-22.09-beta | I5L3PO | python-publicsuffix2 build problem in openEuler:22.09 | 已完成
83 | openEuler-22.09-beta | I5L3PP | python-zope-event build problem in openEuler:22.09 | 已完成
84 | openEuler-22.09-beta | I5L3PQ | yaffs2 build problem in openEuler:22.09 | 已取消
85 | openEuler-22.09-beta | I5L3PR | ibus-m17n build problem in openEuler:22.09 | 已完成
86 | openEuler-22.09-beta | I5L3PS | nodejs-is-builtin-module build problem in openEuler:22.09 | 已取消
87 | openEuler-22.09-beta | I5L3PT | nodejs-traverse build problem in openEuler:22.09 | 已完成
88 | openEuler-22.09-beta | I5L3PU | python-attrs build problem in openEuler:22.09 | 已取消
89 | openEuler-22.09-beta | I5L3PV | python-jwt build problem in openEuler:22.09 | 已取消
90 | openEuler-22.09-beta | I5L3PW | rubygem-activeresource build problem in openEuler:22.09 | 已完成
91 | openEuler-22.09-beta | I5L3PX | rubygem-redis build problem in openEuler:22.09 | 已完成
92 | openEuler-22.09-beta | I5L3PY | ansible-2.9 build problem in openEuler:22.09:Epol | 已完成
93 | openEuler-22.09-beta | I5L3PZ | cobbler build problem in openEuler:22.09:Epol | 已完成
94 | openEuler-22.09-beta | I5L3Q1 | cryptopp build problem in openEuler:22.09:Epol | 已取消
95 | openEuler-22.09-beta | I5L3Q3 | openstack-heat build problem in openEuler:22.09:Epol | 已取消
96 | openEuler-22.09-beta | I5L3Q4 | openstack-ironic-python-agent build problem in openEuler:22.09:Epol | 已完成
97 | openEuler-22.09-beta | I5L3Q5 | openstack-keystone build problem in openEuler:22.09:Epol | 已完成
98 | openEuler-22.09-beta | I5L3Q7 | openstack-placement build problem in openEuler:22.09:Epol | 已完成
99 | openEuler-22.09-beta | I5L3Q8 | openstack-swift build problem in openEuler:22.09:Epol | 已完成
100 | openEuler-22.09-beta | I5L3Q9 | openstack-trove build problem in openEuler:22.09:Epol | 已完成
101 | openEuler-22.09-beta | I5L3QA | python-FormEncode build problem in openEuler:22.09:Epol | 已完成
102 | openEuler-22.09-beta | I5L3QB | python-ibmcclient build problem in openEuler:22.09:Epol | 已完成
103 | openEuler-22.09-beta | I5L3QC | python-ironicclient build problem in openEuler:22.09:Epol | 已完成
104 | openEuler-22.09-beta | I5L3QD | python-jenkins build problem in openEuler:22.09:Epol | 已完成
105 | openEuler-22.09-beta | I5L3QE | python-krest build problem in openEuler:22.09:Epol | 已完成
106 | openEuler-22.09-beta | I5L3QF | python-neutron-lib build problem in openEuler:22.09:Epol | 已完成
107 | openEuler-22.09-beta | I5L3QG | python-neutronclient build problem in openEuler:22.09:Epol | 已完成
108 | openEuler-22.09-beta | I5L3QH | python-openstackclient build problem in openEuler:22.09:Epol | 已完成
109 | openEuler-22.09-beta | I5L3QI | python-os-client-config build problem in openEuler:22.09:Epol | 已完成
110 | openEuler-22.09-beta | I5L3QJ | python-oslo.policy build problem in openEuler:22.09:Epol | 已完成
111 | openEuler-22.09-beta | I5L3QK | python-oslo.vmware build problem in openEuler:22.09:Epol | 已完成
112 | openEuler-22.09-beta | I5L3QL | python-pydotplus build problem in openEuler:22.09:Epol | 已取消
113 | openEuler-22.09-beta | I5L3QM | python-repoze.sphinx.autointerface build problem in openEuler:22.09:Epol | 已完成
114 | openEuler-22.09-beta | I5L3QN | python-sphinx-feature-classification build problem in openEuler:22.09:Epol | 已完成
115 | openEuler-22.09-beta | I5L3QO | python-sphinxcontrib-autoprogram build problem in openEuler:22.09:Epol | 已完成
116 | openEuler-22.09-beta | I5L3QP | python-sphinxcontrib-programoutput build problem in openEuler:22.09:Epol | 已完成
117 | openEuler-22.09-beta | I5L3QR | python-sushy build problem in openEuler:22.09:Epol | 已完成
118 | openEuler-22.09-beta | I5L3QS | python-sushy-oem-idrac build problem in openEuler:22.09:Epol | 已完成
119 | openEuler-22.09-beta | I5L3QT | python-texext build problem in openEuler:22.09:Epol | 已取消
120 | openEuler-22.09-beta | I5L3QU | python-trove-dashboard build problem in openEuler:22.09:Epol | 已取消
121 | openEuler-22.09-beta | I5L3QV | python-vitrageclient build problem in openEuler:22.09:Epol | 已取消
122 | openEuler-22.09-beta | I5L3QW | canal build problem in openEuler:22.09:Epol | 已完成
123 | openEuler-22.09-Dailybuild | I5HVUK | apache-commons-math build problem in openEuler:22.09 | 已完成
124 | openEuler-22.09-Dailybuild | I5HVUZ | ima-evm-utils build problem in openEuler:22.09 | 已完成
125 | openEuler-22.09-Dailybuild | I5HVV6 | pkgship build problem in openEuler:22.09 | 已完成
126 | openEuler-22.09-Dailybuild | I5HVVA | python-iniparse build problem in openEuler:22.09 | 已完成
127 | openEuler-22.09-Dailybuild | I5HZVT | python-iniparse build problem in openEuler:22.09 | 已取消
128 | openEuler-22.09-Dailybuild | I5HZW3 | subunit build problem in openEuler:22.09 | 已完成
129 | openEuler-22.09-Dailybuild | I5I1ZZ | ceph build problem in openEuler:22.09 | 已取消
130 | openEuler-22.09-Dailybuild | I5I60C | python-py build problem in openEuler:22.09 | 已完成
131 | openEuler-22.09-Dailybuild | I5I6MK | libevent build problem in openEuler:22.09 | 已完成
132 | openEuler-22.09-Dailybuild | I5I6MO | libgit2 build problem in openEuler:22.09 | 已完成
133 | openEuler-22.09-Dailybuild | I5IH4X | python-Logbook build problem in openEuler:22.09:Epol | 已完成
134 | openEuler-22.09-Dailybuild | I5IH5G | gpgme build problem in openEuler:22.09 | 已完成
135 | openEuler-22.09-Dailybuild | I5IH62 | criu build problem in openEuler:22.09 | 已完成
136 | openEuler-22.09-Dailybuild | I5IH69 | iotop build problem in openEuler:22.09 | 已完成
137 | openEuler-22.09-Dailybuild | I5IH6D | lensfun build problem in openEuler:22.09 | 已完成
138 | openEuler-22.09-Dailybuild | I5IH6M | libpwquality build problem in openEuler:22.09 | 已完成
139 | openEuler-22.09-Dailybuild | I5IH6T | nftables build problem in openEuler:22.09 | 已完成
140 | openEuler-22.09-Dailybuild | I5IH6Z | python-xgboost build problem in openEuler:22.09 | 已完成
141 | openEuler-22.09-Dailybuild | I5IH8L | system-config-printer build problem in openEuler:22.09 | 已完成
142 | openEuler-22.09-Dailybuild | I5IHR8 | firefox build problem in openEuler:22.09 | 已完成
143 | openEuler-22.09-Dailybuild | I5ILKE | sssd build problem in openEuler:22.09 | 已完成
144 | openEuler-22.09-Dailybuild | I5IQZF | highlight build problem in openEuler:22.09:Epol | 已完成
145 | openEuler-22.09-Dailybuild | I5IUF9 | bolt build problem in openEuler:22.09 | 已完成
146 | openEuler-22.09-Dailybuild | I5IUGH | cups build problem in openEuler:22.09 | 已完成
147 | openEuler-22.09-Dailybuild | I5IUHD | rubygem-redis build problem in openEuler:22.09 | 已完成
148 | openEuler-22.09-Dailybuild | I5J0YO | chrony build problem in openEuler:22.09 | 已完成
149 | openEuler-22.09-Dailybuild | I5J0YT | ldns build problem in openEuler:22.09 | 已完成
150 | openEuler-22.09-Dailybuild | I5JH5V | gawk build problem in openEuler:22.09 | 已完成
151 | openEuler-22.09-Kernel | I5ITI6 | 【arm】ltp用例tcp6-multi-diffip11执行失败产生softlockup问题 | 待办的
152 | openEuler-22.09-round-1 | I5HZVX | folks build problem in openEuler:22.09 | 已完成
153 | openEuler-22.09-round-1 | I5K0NK | 【arm】ltp用例tcp6-multi-diffip11执行失败产生softlockup问题 | 待办的
154 | openEuler-22.09-round-1 | I5KMKI | chrony build problem in openEuler:22.09 | 已完成
155 | openEuler-22.09-round-1 | I5KMKL | hadoop-3.1 build problem in openEuler:22.09 | 待办的
156 | openEuler-22.09-round-1 | I5KR3D | 【安装冲突arm】openEuler:22.09分支安装mysql-server时，报与greatsql冲突 | 已取消
157 | openEuler-22.09-round-1 | I5KTVM | caja-extensions is unresolvable in openEuler:22.09:Epol | 待办的
158 | openEuler-22.09-round-1 | I5KTX5 | octave is unresolvable in openEuler:22.09:Epol | 待办的
159 | openEuler-22.09-round-1 | I5L3PB | etcd build problem in openEuler:22.09 | 已完成
160 | openEuler-22.09-round-1 | I5L3PE | libuv build problem in openEuler:22.09 | 已完成
161 | openEuler-22.09-round-1 | I5L3PG | mysql5 build problem in openEuler:22.09 | 待办的
162 | openEuler-22.09-round-1 | I5L3PL | python-crypto build problem in openEuler:22.09 | 待办的
163 | openEuler-22.09-round-1 | I5L3QQ | python-sphobjinv build problem in openEuler:22.09:Epol | 已完成
164 | openEuler-22.09-round-1 | I5LGJS | 【22.09 RC1】【arm/x86】skylark安装时有异常告警，并且无法成功卸载 | 已验收
165 | openEuler-22.09-round-1 | I5LGXT | 【22.09_RC1_EPOL】【arm/x86】redshift卸载时报错redshift.servic.service不存在 | 已验收
166 | openEuler-22.09-round-1 | I5LHHY | 【22.09_RC1_EPOL】【arm/x86】openstack-ceilometer-ipmi安装报错：Failed to preset unit: Unit file openstack-ceilometer-alarm-ipmi.service does not exist | 修复中
167 | openEuler-22.09-round-1 | I5LI5A | 【22.09_RC1_EPOL】【arm/x86】dde-control-center安装卸载存在异常信息 | 已验收
168 | openEuler-22.09-round-1 | I5LIIJ | python-texext is unresolvable in openEuler:22.09:Epol | 已完成
169 | openEuler-22.09-round-1 | I5LIIW | gssdp build problem in openEuler:22.09 | 已完成
170 | openEuler-22.09-round-1 | I5LIJI | curl build problem in openEuler:22.09 | 已完成
171 | openEuler-22.09-round-1 | I5LILE | galera build problem in openEuler:22.09 | 已完成
172 | openEuler-22.09-round-1 | I5LJ2K | 【22.09 RC1】【arm/x86】使用vi编辑文件，无法直接进入文件，报错：E1187: Failed to source defaults.vim | 已验收
173 | openEuler-22.09-round-1 | I5LK9U | dovecot build problem in openEuler:22.09 | 已完成
174 | openEuler-22.09-round-1 | I5LKAJ | gd build problem in openEuler:22.09 | 已完成
175 | openEuler-22.09-round-1 | I5LKAX | vdsm-jsonrpc-java build problem in openEuler:22.09:Epol | 已完成
176 | openEuler-22.09-round-1 | I5LKRM | so使用大页显示 anon_hugepage (deleted) | 已完成
177 | openEuler-22.09-round-1 | I5LLLW | 【22.09 RC1】【arm/x86】oech.service服务启动失败 | 已验收
178 | openEuler-22.09-round-1 | I5LMDA | 【22.09 RC1】【arm/x86】hive安装失败，mysql5-server与greatsql-server有冲突 | 待办的
179 | openEuler-22.09-round-1 | I5LMDP | 【22.09_RC1_EPOL】【x86】安装ovirt-host包缺少依赖导致无法安装 | 已完成
180 | openEuler-22.09-round-1 | I5LMJ4 | 加载环境变量LD_HUGEPAGE_LIB=1，动态库so未使用大页内存 | 已验收
181 | openEuler-22.09-round-1 | I5LN60 | 【22.09 RC1】【arm/x86】storm-nimbus.service服务stop失败，返回状态码143 | 待办的
182 | openEuler-22.09-round-1 | I5LNBR | 【22.09 RC1】【arm/x86】storm-supervisor.service服务stop失败，返回状态码143 | 待办的
183 | openEuler-22.09-round-1 | I5LNU7 | 【22.09_RC1_EPOL】【arm/x86】setroubleshoot-server包安装缺少依赖 | 已验收
184 | openEuler-22.09-round-1 | I5LQP4 | [22.09-RC1][aarch64/x86_64]安装完成后输入命令“yum grouplist hidden”回显缺少“Installed Environment Groups” 和 “Installed Groups”子项 | 已完成
185 | openEuler-22.09-round-1 | I5LRDA | kernel build problem in openEuler:22.09 | 已完成
186 | openEuler-22.09-round-1 | I5LRMC | kata-containers build problem in openEuler:22.09 | 已完成
187 | openEuler-22.09-round-1 | I5LRS2 | ironjacamar build problem in openEuler:22.09 | 已完成
188 | openEuler-22.09-round-1 | I5LRUP | kernel:raspberrypi-kernel build problem in openEuler:22.09 | 已完成
189 | openEuler-22.09-round-1 | I5LRWD | perl-ExtUtils-Install build problem in openEuler:22.09 | 已完成
190 | openEuler-22.09-round-1 | I5LRYB | perl-Test-NoWarnings build problem in openEuler:22.09 | 已完成
191 | openEuler-22.09-round-1 | I5LRZL | plexus-utils build problem in openEuler:22.09 | 已完成
192 | openEuler-22.09-round-1 | I5LS0G | xnio build problem in openEuler:22.09 | 已完成
193 | openEuler-22.09-round-1 | I5LSN4 | 【22.09 RC1】【arm】rasdaemon.service服务启动失败并产生core | 已完成
194 | openEuler-22.09-round-1 | I5LT5D | 【22.09 RC1】【arm/x86】atuned.service服务启动失败 | 已验收
195 | openEuler-22.09-round-1 | I5LTBC | 【22.09 RC1】【arm/x86】atune-engine.service服务启动失败，报错”ImportError: cannot import name 'MaskedArray' from 'sklearn.utils.fixes'“ | 已验收
196 | openEuler-22.09-round-1 | I5LWF6 | 【22.09 RC1 】【arm/x86 】iptables.service ip6tables.service服务stop之后日志中有报错：“Setting chains to policy ACCEPT: nat mangle raw security filter [FAILED]” | 已验收
197 | openEuler-22.09-round-1 | I5LX04 | startxfce4无法正常启动xfce桌面环境 | 已取消
198 | openEuler-22.09-round-1 | I5LX3Y | 开启该特性进行perf调试，有报错 | 待办的
199 | openEuler-22.09-round-1 | I5LYYF | 【22.09 RC1 】【arm/x86 】firebird-superserver.service服务启动之后，日志中有提示“Can't open PID file /run/firebird/default.pid” | 已验收
200 | openEuler-22.09-round-1 | I5LZVC | mailman build problem in openEuler:22.09 | 已完成
201 | openEuler-22.09-round-1 | I5LZWF | nodejs-defence-cli build problem in openEuler:22.09 | 已完成
202 | openEuler-22.09-round-1 | I5LZXD | openldap build problem in openEuler:22.09 | 已挂起
203 | openEuler-22.09-round-1 | I5LZZR | python-cairocffi build problem in openEuler:22.09 | 已完成
204 | openEuler-22.09-round-1 | I5M00E | rubygem-redis build problem in openEuler:22.09 | 已完成
205 | openEuler-22.09-round-1 | I5M0ZP | [22.09][arm/x86]apache与tomaca组合场景报错jar包找不到 | 已验收
206 | openEuler-22.09-round-1 | I5M3W4 | [22.09-RC1][aarch64/x86_64]Postman停止gala-gopher插件失败 | 已验收
207 | openEuler-22.09-round-1 | I5M48E | 【22.09_round1】【x86/arm】卸载gopher插件后，获取插件运行信息接口返回500 | 已验收
208 | openEuler-22.09-round-1 | I5M5EQ | 【22.09 RC1 】【arm/x86 】lorax-composer.service服务启动失败，日志中报错：“ValueError: The name 'v0_routes' is already registered for this blueprint” | 已验收
209 | openEuler-22.09-round-1 | I5M6BS | 【22.09-RC1】【x86/arm】tensorflow源码包本地自编译失败 | 待办的
210 | openEuler-22.09-round-1 | I5M6DY | 【22.09-RC1】【x86/arm】texlive-split-s源码包checksum doesn't match | 已验收
211 | openEuler-22.09-round-1 | I5M7WB | 【22.09-RC1】【x86】curl自编译依赖glibc-debuginfo，但是该软件包不在OS和everything源中，而在debuginfo源，不太合理 | 已取消
212 | openEuler-22.09-round-1 | I5M7WO | 【22.09-RC1】【x86】glibc自编译失败，testsuite_whitelist.x86_64文件损坏 | 已验收
213 | openEuler-22.09-round-1 | I5M8W7 | 【22.09-RC1】【codedb】-O3 -flto -fipa-struct-reorg=1 -flto-partition=one编译vtk ICE:lto1: internal compiler error(at dwarf2out.c:31353) | 待办的
214 | openEuler-22.09-round-1 | I5M9YN | 【22.09_RC1】【x86/arm】aops-manager服务启动失败 | 已完成
215 | openEuler-22.09-round-1 | I5MCLO | 【22.09 RC1 】【arm/x86 】在python3中执行from skopt import Optimizer，报错：“ImportError: cannot import name 'MaskedArray' from 'sklearn.utils.fixes'” | 已验收
216 | openEuler-22.09-round-1 | I5ME2Y | 【22.09-RC1】【x86/arm】上执行命令doxygen -w rtf rtf-mode，命令返回值为1 | 已完成
217 | openEuler-22.09-round-1 | I5MEV7 | [22.09][arm物理机]u盘选择Test this media模式安装，安装过程报错 | 已验收
218 | openEuler-22.09-round-1 | I5MG3H | 【22.09 RC1 】【arm/x86 】patch-tracking.service服务启动失败 | 已取消
219 | openEuler-22.09-round-1 | I5MGFX | [22.09 RC1] [arm/X86] 执行podman create --add-host host:192.168.122.172 alpine命令后，没有生成create-config文件 | 待办的
220 | openEuler-22.09-round-1 | I5MGGV | 【22.09 RC1 】【arm/x86 】systemd-time-wait-sync.service服务启动超时 | 已取消
221 | openEuler-22.09-round-1 | I5MHI2 | 【openEuler22.09】【arm/x86】ltp执行epoll_pwait的4个用例失败 | 待办的
222 | openEuler-22.09-round-1 | I5MHRB | [openEuler-22.09] kernel仓CI 构建报internal compiler error | 已完成
223 | openEuler-22.09-round-1 | I5MIRX | 【22.09-RC1】【x86/arm】unique源码包checksum doesn't match | 已验收
224 | openEuler-22.09-round-1 | I5MIUF | 【22.09 RC1 】【arm/x86 】stap-exporter.service服务启动之后，提示信息“Checking "/lib/modules/5.10.0-106.2.0.56.oe2209.aarch64/build/.config" failed with error: No such file or directory” | 已取消
225 | openEuler-22.09-round-1 | I5MJ24 | 【22.09 RC1 】【arm/x86 】corosync-qdevice.service服务stop失败并产生core | 待办的
226 | openEuler-22.09-round-1 | I5MJAA | [22.09]spec文件存在软件包编译依赖自身，且打包包含系统环境文件 | 已验收
227 | openEuler-22.09-round-1 | I5MJR3 | [22.09]spec文件存在软件包打包包含系统环境文件 | 已完成
228 | openEuler-22.09-round-1 | I5MJR6 | 【22.09 RC1 】【arm/x86 】kubelet.service做完服务起停之后，journalctl -u kubelet.service存在失败日志 | 已取消
229 | openEuler-22.09-round-1 | I5MJW1 | 【22.09 RC1 】【arm/x86 】kube-apiserver.service做完服务起停之后，journalctl -u kube-apiserver.service存在失败日志 | 已取消
230 | openEuler-22.09-round-1 | I5MK32 | 【22.09 RC1 】【arm/x86 】kube-controller-manager.service做完服务起停之后，journalctl -u kube-controller-manager.service存在失败日志 | 已取消
231 | openEuler-22.09-round-1 | I5MKDT | babeltrace build problem in openEuler:22.09 | 已完成
232 | openEuler-22.09-round-1 | I5MKFA | gdisk build problem in openEuler:22.09 | 已完成
233 | openEuler-22.09-round-1 | I5MKIJ | jackson-databind build problem in openEuler:22.09 | 已完成
234 | openEuler-22.09-round-1 | I5MKKP | jackson-dataformats-text build problem in openEuler:22.09 | 已完成
235 | openEuler-22.09-round-1 | I5MKM3 | libuser build problem in openEuler:22.09 | 已完成
236 | openEuler-22.09-round-1 | I5MKTM | python-Pympler build problem in openEuler:22.09:Epol | 已完成
237 | openEuler-22.09-round-1 | I5MLFW | 在openEuler-22.09分支缺安装依赖 | 已完成
238 | openEuler-22.09-round-1 | I5MNBL | [22.09RC1 arm/x86] podman export -o redis-container.tar id 提示archive/tar: sockets not supported | 待办的
239 | openEuler-22.09-round-1 | I5MNNT | [22.09RC1 arm/x86] podman create --blkio-weight 15 alpine ls 提示Your kernel does not support Block I/O weight or the cgroup is not mounted. Weight discarded. | 待办的
240 | openEuler-22.09-round-1 | I5MOHA | ntp build problem in openEuler:22.09 | 已完成
241 | openEuler-22.09-round-1 | I5MSBI | 【22.09 RC1】【arm/x86】samba.service服务执行stop操作之后状态为failed | 已取消
242 | openEuler-22.09-round-1 | I5MTA9 | [22.09]默认未安装gcc | 待办的
243 | openEuler-22.09-round-1 | I5N07H | glassfish-hk2 build problem in openEuler:22.09 | 已完成
244 | openEuler-22.09-round-1 | I5N07O | kernel:kernel-rt build problem in openEuler:22.09 | 已完成
245 | openEuler-22.09-round-1 | I5N07T | zeromq build problem in openEuler:22.09 | 已完成
246 | openEuler-22.09-round-1 | I5N07X | rubygem-sprockets-rails build problem in openEuler:22.09 | 已完成
247 | openEuler-22.09-round-1 | I5N08C | rubygem-thin build problem in openEuler:22.09 | 已完成
248 | openEuler-22.09-round-2 | I5JAWA | 【22.09 arm/x86】 llvm安装卸载后，出现告警信息：/sbin/ldconfig: /usr/lib64/libLLVM-10.so is not a symbolic link | 已完成
249 | openEuler-22.09-round-2 | I5JH62 | crash build problem in openEuler:22.09 | 已完成
250 | openEuler-22.09-round-2 | I5MGZ0 | 【openEuler 22.09】chpasswd命令执行报错 | 已完成
251 | openEuler-22.09-round-2 | I5MU0F | 【22.09】智能运维Aops，部署gala-gopher三天后，tcp探针进程退出，未重新拉起 | 已完成
252 | openEuler-22.09-round-2 | I5MUWA | 【22.09】智能运维Aops，gala-anteater usage中存在无用参数TRIGGER_TYPE待删除，且DURATION设置参数未生效待修改 | 已完成
253 | openEuler-22.09-round-2 | I5MYIJ | python-uhashring build problem in openEuler:22.09:Epol | 待办的
254 | openEuler-22.09-round-2 | I5N1YC | 1、kbimg.sh脚本入参异常时未打印usage信息；2、kbimg.sh脚本-b参数没有校验路径有效性 | 已完成
255 | openEuler-22.09-round-2 | I5N2ED | kbimg.sh在并发场景下会做多余的umount和rm清理动作 | 已完成
256 | openEuler-22.09-round-2 | I5N89Y | 1. kbimg.sh脚本未清理initramfs.img；2. PXE安装物理机失败，原因是找不到磁盘和网卡 | 已完成
257 | openEuler-22.09-round-2 | I5NC5K | [22.09 RC2 arm/x86] mariadb-server包安装与greatsql-server冲突 | 已完成
258 | openEuler-22.09-round-2 | I5NC97 | libcap build problem in openEuler:22.09 | 已完成
259 | openEuler-22.09-round-2 | I5NCBL | rubygem-hiredis build problem in openEuler:22.09 | 待办的
260 | openEuler-22.09-round-2 | I5NCFL | xnio build problem in openEuler:22.09 | 已完成
261 | openEuler-22.09-round-2 | I5NCO5 | libpwquality build problem in openEuler:22.09 | 已完成
262 | openEuler-22.09-round-2 | I5ND9V | 【22.09】智能运维Aops，gala-inference gala-spider安装包升级后，yaml配置文件未保留配置 | 已完成
263 | openEuler-22.09-round-2 | I5NDY1 | [22.09 RC2 arm/x86] rpcclient ${NODE2_IPV4} -U "testsamba" -c 'netshareenum‘ 报错Cannot connect to server. Error was NT_STATUS_NOT_FOUND | 已完成
264 | openEuler-22.09-round-2 | I5NDZF | docker格式转化成的镜像/etc/hosts文件为空 | 已完成
265 | openEuler-22.09-round-2 | I5NE1S | kbimg.sh裁剪后PXE安装的物理机，没有/etc/resolv.conf文件 | 已挂起
266 | openEuler-22.09-round-2 | I5NE6G | 【22.09-RC2】【arm】zlib源码包本地自编译失败，缺少部分补丁0001-Neon-Optimized-hash-chain-rebase.patch | 已完成
267 | openEuler-22.09-round-2 | I5NF8Y | 【22.09 RC2 】【x86 】fence_virtd.service服务stop失败，状态为failed（arm环境没有此问题） | 已完成
268 | openEuler-22.09-round-2 | I5NFC5 | [22.09 RC2 arm/x86] mysql/mysql-server/mysql5装包提示与greatsql冲突 | 已完成
269 | openEuler-22.09-round-2 | I5NFOD | docker格式转化成的镜像/sys挂载异常 | 已完成
270 | openEuler-22.09-round-2 | I5NFRC | kbimg.sh脚本未校验Global.cfg配置有效性 | 已完成
271 | openEuler-22.09-round-2 | I5NFZ4 | kylin-video升级到3.1.3，UKUI上版本信息和实际安装的不一致 | 已完成
272 | openEuler-22.09-round-2 | I5NG1R | 主体为默认模式，关于背景为黑色，应该为白色 | 已完成
273 | openEuler-22.09-round-2 | I5NHM1 | protobuf-c build problem in openEuler:22.09 | 已完成
274 | openEuler-22.09-round-2 | I5NHPS | rubygem-nio4r build problem in openEuler:22.09 | 已完成
275 | openEuler-22.09-round-2 | I5NHV3 | zeromq build problem in openEuler:22.09 | 已完成
276 | openEuler-22.09-round-2 | I5NJ0V | [22.09-RC2][x86/aarch][aops]首次登录，gala-gopher插件的前后台状态不一致 | 已挂起
277 | openEuler-22.09-round-2 | I5NJ3R | [22.09-RC2][x86/aarch][aops]建议“建议开启采集项“只适用于当前未开启采集项的项目 | 已完成
278 | openEuler-22.09-round-2 | I5NJ3Z | 【22.09_RC2】【x86/arm】aops-manager刪除主机失败，提示request parameter error | 已完成
279 | openEuler-22.09-round-2 | I5NJG3 | proxy未将imageType值传递给os-agent | 已完成
280 | openEuler-22.09-round-2 | I5NLQC | [22.09-RC2][x86/aarch][aops]删除host,表host_group的host_count字段数量不变 | 已完成
281 | openEuler-22.09-round-2 | I5NLZI | 【openEuler 22.09 rc2】启动器中个别应用图标显示异常 | 待办的
282 | openEuler-22.09-round-2 | I5NNMO | 【22.09-RC2】【x86/arm】modprobe -f报错：ERROR: could not insert 'dm_cache': Key was rejected by service | 已挂起
283 | openEuler-22.09-round-2 | I5NOIG | 【22.09 RC2 】【arm/x86 】执行sudo -u hdfs hdfs namenode -format报错：“java.lang.ClassNotFoundException: org.apache.hadoop.thirdparty.com.google.common.base.Preconditions” | 待办的
284 | openEuler-22.09-round-2 | I5NORC | [openEuler-22.09][Yoga]Glance报错No module named 'oslo_limit‘ | 已完成
285 | openEuler-22.09-round-2 | I5NP5U | booth build problem in openEuler:22.09:Epol | 已验收
286 | openEuler-22.09-round-2 | I5NP6A | kiran-cc-daemon build problem in openEuler:22.09:Epol | 待办的
287 | openEuler-22.09-round-2 | I5NP88 | 【22.09_RC2】【x86/arm】aops-manager删除插件后，建议前端不展示插件信息 | 已完成
288 | openEuler-22.09-round-2 | I5NS6C | 【22.09】智能运维Aops，gala-anteater故障检测存在大量误报 | 已完成
289 | openEuler-22.09-round-2 | I5NTZX | 用不同架构的镜像升级，升级失败，手动切换启动项回退失败，报错找不到内核 | 已挂起
290 | openEuler-22.09-round-2 | I5NU2Y | docker镜像升级的掉电场景，kubeos-temp等残留资源未清理干净，导致重试升级失败 | 已挂起
291 | openEuler-22.09-round-2 | I5NU58 | KubeOS升级不支持legacy | 已完成
292 | openEuler-22.09-round-2 | I5NWYO | 【22.09-RC2】【arm/x86】python-crypto源码包本地自编译失败 | 待办的
293 | openEuler-22.09-round-2 | I5NYI4 | libmicrohttpd build problem in openEuler:22.09 | 已完成
294 | openEuler-22.09-round-2 | I5NYIP | elixir build problem in openEuler:22.09 | 已完成
295 | openEuler-22.09-round-2 | I5NYK6 | postgresql build problem in openEuler:22.09 | 待办的
296 | openEuler-22.09-round-2 | I5NYKW | rubygem-connection_pool build problem in openEuler:22.09 | 已完成
297 | openEuler-22.09-round-2 | I5NYZV | 物理机节点升级后，/boot/efi/目录下为空 | 已挂起
298 | openEuler-22.09-round-2 | I5O2GJ | 【22.09-RC2】【arm/x86】thrift源码包本地自编译失败 | 待办的
299 | openEuler-22.09-round-2 | I5O2LX | 【22.09_RC2】【x86/arm】使用aops-tools工具部署agent，建议自动在目标机器上安装依赖软件包，如：python3-libselinux | 已完成
300 | openEuler-22.09-round-2 | I5O2NG | kbimg.sh vm-image和pxe-image模式下的最小磁盘空间要求都是5G，和资料规格不符 | 已挂起
301 | openEuler-22.09-round-2 | I5O2TI | 【22.09-RC2】【x86】giflib源码包本地自编译失败 | 已完成
302 | openEuler-22.09-round-2 | I5O2WN | 【openEuler 22.09】【备份还原】备份系统完成后有错误提示 | 已完成
303 | openEuler-22.09-round-2 | I5O33P | 【22.09-RC2】【arm/x86】eclipse源码包本地自编译失败 | 已完成
304 | openEuler-22.09-round-2 | I5O3LE | 【openEuler 22.09】【备份还原】全局还原和系统还原时有错误提示 | 已完成
305 | openEuler-22.09-round-2 | I5OBZD | dm-thin长稳压力测试时pvscan发生segfault | 待办的
306 | openEuler-22.09-round-2 | I5ODCF | ksh build problem in openEuler:22.09 | 已完成
307 | openEuler-22.09-round-2 | I5ODDF | libfprint build problem in openEuler:22.09 | 待办的
308 | openEuler-22.09-round-2 | I5ODDK | python-httpretty build problem in openEuler:22.09 | 已确认
309 | openEuler-22.09-round-2 | I5ODDV | socket_wrapper build problem in openEuler:22.09 | 已完成
310 | openEuler-22.09-round-2 | I5ODEY | k3s build problem in openEuler:22.09:Epol | 已完成
311 | openEuler-22.09-round-2 | I5OER4 | 【fuzz】sleuthkit --sanitizer address heap-buffer-overflow on address | 待办的
312 | openEuler-22.09-round-2 | I5OFD1 | gdk-pixbuf2 build problem in openEuler:22.09 | 待办的
313 | openEuler-22.09-round-2 | I5OFD2 | gupnp build problem in openEuler:22.09 | 已完成
314 | openEuler-22.09-round-2 | I5OFD7 | kernel-rt and raspberrypi-kernel-rt build problem in openEuler:22.09 | 待办的
315 | openEuler-22.09-round-2 | I5OKU0 | 【22.09】【nvwa】服务启动失败时，返回值为0 | 待办的
316 | openEuler-22.09-round-3 | I5OV2X | 【openEuler-22.09-RC3 】[arm/x86]traffic_layout remove core dump | 待办的