## Sheet1
里程碑 | 任务标题 | 任务负责人 | 任务状态 | 标签 | 任务路径
openEuler-20.03-LTS-SP3-round-1 | 【SP3-arm/x86】全量操作中bind包调用selinx-policy导致升级、降级报错 | Hugel | 待办的 |  | https://gitee.com/open_euler/dashboard?issue_id=I4KR8A
openEuler-20.03-LTS-SP3-round-2 | 【20.03 SP3】【x86 物理机】从SP3全量降级到LTS的过程中，物理机连接中断，无法继续降级 | 卢杰 | 待办的 |  | https://gitee.com/open_euler/dashboard?issue_id=I4LIGZ
openEuler-20.03-LTS-SP3-round-2 | [20.03-LTS-SP3]arm物理机u盘安装后，message报错arm-smmu-v3 arm-smmu-v3.0.auto: enable smmu mpam failed | 裘来彬 | 待办的 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4LMGH
openEuler-20.03-LTS-SP3-round-2 | 【openEuler20.03 LTS SP3】【ARM/X86】KASAN模式执行syskaller用例，产生一些问题。 | 裘来彬 | 待办的 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4LWI8
openEuler-20.03-LTS-SP3-round-3 | mem_size overflow in sdsMakeRoomFor | small_leek | 待办的 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4G5Y3
openEuler-20.03-LTS-SP3-round-3 | Unexpect-shift in op_rescale64 | small_leek | 待办的 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4JH69
openEuler-20.03-LTS-SP3-round-3 | [20.03-lts-Sp3 round3-X86] powertop2tuned提示版本过低 | 周文培 | 待办的 | sig/Computing | https://gitee.com/open_euler/dashboard?issue_id=I4M2YM
openEuler-20.03-LTS-SP3-round-3 | 【openEuler20.03 LTS SP3】【ARM/X86】UBSAN模式执行syskaller用例，产生一些问题。 | 裘来彬 | 待办的 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4M5DO
openEuler-20.03-LTS-SP3-round-3 | 【20.03 LTS SP3】【arm】ovn-northd.service服务反复重启之后，日志中打印“send error”、“receive error”相关信息 | small_leek | 待办的 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4M61R
openEuler-20.03-LTS-SP3-round-3 | 【20.03-LTS-SP3】【arm/x86】openvswitch-ipsec.service启动日志中存在ipsec.service启动失败信息，且导致ipsec.service无法成功启动 | small_leek | 待办的 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4M8FM
openEuler-20.03-LTS-SP3-round-3 | sp3版本中openEuler-latest内容与实际不符 | small_leek | 待办的 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4M92Z
openEuler-20.03-LTS-SP3-round-3 | 【20.03 SP3】【x86物理机】sp1升级到sp1 update，然后升级到sp3，reboot后有报错：Error: rpmdb open failed | panxh_purple | 待办的 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4MC30
openEuler-20.03-LTS-SP3-round-3 | 【20.03 SP3】LTS全量升级到SP3，reboot后执行全量降级，降级结束后一段时间后有报错打印：awk: error while loading shared libraries: libtinfo.so.6: cannot open shared object file: No such file or directory，机器无法ssh连接 | 朱俊豪 | 待办的 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4MC4O
openEuler-20.03-LTS-SP3-round-3 | 【fuzz】sleuthkit_fls_ntfs_fuzzer heap-buffer-overflow | small_leek | 待办的 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4MGLC
openEuler-20.03-LTS-SP3-round-1 | [20.03 LTS SP3][Train]openstack-neutron缺少依赖dibbler-client | huangtianhua | 已完成 | sig/sig-openstack | https://gitee.com/open_euler/dashboard?issue_id=I4JH6S
openEuler-20.03-LTS-SP3-round-1 | [20.03 LTS SP3][Train]openstack-nova缺少python-monotonic依赖 | huangtianhua | 已完成 | sig/sig-openstack | https://gitee.com/open_euler/dashboard?issue_id=I4JNRA
openEuler-20.03-LTS-SP3-round-1 | [20.03 LTS SP3][Train]openstack-neutron缺少python-os-xenapi | huangtianhua | 已完成 | sig/sig-openstack | https://gitee.com/open_euler/dashboard?issue_id=I4JNT7
openEuler-20.03-LTS-SP3-round-1 | 【x86】sp2升级到sp3时sgx-pck-id-retrieval-tool有告警信息 | 王城 | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4JQEQ
openEuler-20.03-LTS-SP3-round-1 | SP3分支rubygem-sinatra代码构建失败 | small_leek | 已完成 | sig/sig-ruby | https://gitee.com/open_euler/dashboard?issue_id=I4JQOB
openEuler-20.03-LTS-SP3-round-1 | SP3分支rubygem-rack-test代码构建失败 | small_leek | 已完成 | sig/sig-ruby | https://gitee.com/open_euler/dashboard?issue_id=I4JQOD
openEuler-20.03-LTS-SP3-round-1 | SP3分支rubygem-rack-protection代码构建失败 | small_leek | 已完成 | sig/sig-ruby | https://gitee.com/open_euler/dashboard?issue_id=I4JQOG
openEuler-20.03-LTS-SP3-round-1 | 【x86】sp3降级到sp2时cyrus-sasl-gssapi与cyrus-sasl报冲突 | yixiangzhike | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4JQPB
openEuler-20.03-LTS-SP3-round-1 | openEuler 20.03 SP3中libxml2-2.9.10-22版本库存在问题，导致clufter软件包编译失败 | panxh_purple | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4JQPH
openEuler-20.03-LTS-SP3-round-1 | 【x86】sp3降级到sp2时groff与groff-base报文件冲突 | tianwei | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4JQPU
openEuler-20.03-LTS-SP3-round-1 | 【x86】sp3降级到sp2时abseil-cpp与grpc冲突 | Monday | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4JQRC
openEuler-20.03-LTS-SP3-round-1 | [x86]sgxsdk从sp3降级到sp2告警 | 王城 | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4JQZJ
openEuler-20.03-LTS-SP3-round-1 | 【x86】rdma-core从sp3降级到sp2告警 | 孙苏皖 | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4JR0U
openEuler-20.03-LTS-SP3-round-1 | [x86] tog-pegasus-help从sp3降级到sp2时有告警信息 | small_leek | 已完成 | sig/System-tool | https://gitee.com/open_euler/dashboard?issue_id=I4JS4I
openEuler-20.03-LTS-SP3-round-1 | 【arm】cups从sp3降级到sp2告警 | shirely | 已完成 | sig/Desktop | https://gitee.com/open_euler/dashboard?issue_id=I4JSLU
openEuler-20.03-LTS-SP3-round-1 | 【arm/x86】jack-audio-connection-kit从sp3降级到sp2告警 | small_leek | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4JSMI
openEuler-20.03-LTS-SP3-round-1 | 【arm/x86】bind-chroot从sp3降级到sp2告警 | 蒋恒 | 已完成 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4JSOA
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm物理机】最小化安装选择部分插件（容器管理 、开发工具），日志中有告警 | 吴鹏 | 已完成 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4JXOF
openEuler-20.03-LTS-SP3-round-1 | 【sp3-x86】安装子包sgx-dcap-pccs出现告警信息 |  | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K2AY
openEuler-20.03-LTS-SP3-round-1 | [SP3 util-linux] mount命令挂载提示：unable to apply new capability set | shangyibin | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4K9WR
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】执行dovecot-sysreport命令报错 | small_leek | 已完成 | sig/Application | https://gitee.com/open_euler/dashboard?issue_id=I4KD1B
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】执行clamonacc -w命令报错 | small_leek | 已完成 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4KH5Z
openEuler-20.03-LTS-SP3-round-1 | [20.03 LTS SP3][Train]openstack-heat-engine服务启动失败 | huangtianhua | 已完成 | sig/sig-openstack | https://gitee.com/open_euler/dashboard?issue_id=I4KI3Q
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm 物理机】SP1向SP3全量升级，出现avahi子包冲突问题 | zhanzhimin | 已完成 | sig/Desktop | https://gitee.com/open_euler/dashboard?issue_id=I4KIFU
openEuler-20.03-LTS-SP3-round-2 | [20.03 LTS SP3][Train] python-lz4构建失败 | huangtianhua | 已完成 | sig/sig-openstack | https://gitee.com/open_euler/dashboard?issue_id=I4KWHY
openEuler-20.03-LTS-SP3-round-2 | 【20.03 LTS SP3】redis-sentinel命令提示需要sentinel.conf与实际不符 | small_leek | 已完成 | sig/sig-ai-bigdata | https://gitee.com/open_euler/dashboard?issue_id=I4L2P5
openEuler-20.03-LTS-SP3-round-2 | 【SP3-arm/x86】abrt-addon-ccpp从SP2升级到SP3有异常信息 | small_leek | 已完成 | sig/Application | https://gitee.com/open_euler/dashboard?issue_id=I4L3G5
openEuler-20.03-LTS-SP3-round-2 | 【20.03-LTS-SP3】【x86/arm】zlib源码包本地自编译失败 | small_leek | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4L3J0
openEuler-20.03-LTS-SP3-round-2 | 【20.03 SP3】【arm/x86】fakeroot-help从sp3向sp1降级有失败信息 | 邹林 | 已完成 |  | https://gitee.com/open_euler/dashboard?issue_id=I4L3Y3
openEuler-20.03-LTS-SP3-round-2 | 【20.03 SP3】【arm物理机】SP3全量降级时在进行glibc-common的降级时，全量降级进程突然中断，glibc-common单包降级有报错 | 任宏勋 | 已完成 | sig/Computing | https://gitee.com/open_euler/dashboard?issue_id=I4L435
openEuler-20.03-LTS-SP3-round-2 | 【openEuler 20.03 SP3 Test round 2 】【x86/arm】帮助手册内容显示异常 |  | 已完成 | sig/sig-DDE | https://gitee.com/open_euler/dashboard?issue_id=I4L9F3
openEuler-20.03-LTS-SP3-round-2 | 【openEuler20.03 LTS SP3 RC2】【ARM】执行长稳sysfs用例中断，产生core文件。 | 成坚 | 已完成 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4LD5U
openEuler-20.03-LTS-SP3-round-2 | 【20.03-LTS-SP3】【x86/arm】thrift源码包本地自编译失败 | small_leek | 已完成 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4LI21
openEuler-20.03-LTS-SP3-round-2 | [20.03-LTS-SP3]安装OS时主机名设置64字符保存成功，自定义磁盘分区时报主机名无效的错误 | yanan-rock | 已完成 | sig/sig-OS-Builder | https://gitee.com/open_euler/dashboard?issue_id=I4LKO5
openEuler-20.03-LTS-SP3-round-2 | 20.03-LTS-SP3测试环境openstack的虚拟机创建失败 | 邢超超 | 已完成 | sig/Virt | https://gitee.com/open_euler/dashboard?issue_id=I4LQBP
openEuler-20.03-LTS-SP3-round-3 | Abort in op_pcm_seek_page | small_leek | 已完成 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4JH3K
openEuler-20.03-LTS-SP3-round-3 | 【20.03-LTS-SP3】【x86/arm】findbugs源码包本地自编译失败 | small_leek | 已完成 | sig/sig-Java | https://gitee.com/open_euler/dashboard?issue_id=I4M1Y9
openEuler-20.03-LTS-SP3-round-3 | 【20.03-LTS-SP3】【x86/arm】narayana源码包本地自编译失败 | small_leek | 已完成 | sig/sig-Java | https://gitee.com/open_euler/dashboard?issue_id=I4M1YJ
openEuler-20.03-LTS-SP3-round-3 | 【fuzz测试】堆溢出 | small_leek | 已完成 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4M3MM
openEuler-20.03-LTS-SP3-round-3 | 【20.03 LTS SP3】【arm/x86】initial-setup从SP2到SP3及从SP2到SP2_update最新版到SP3升级有错误 | small_leek | 已完成 | sig/System-tool | https://gitee.com/open_euler/dashboard?issue_id=I4MCP6
openEuler-20.03-LTS-SP3-round-1 | iSulad从sp2升级到sp3有告警日志 |  | 已验收 | sig/iSulad | https://gitee.com/open_euler/dashboard?issue_id=I4JOTA
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm物理机】最小化安装，手动配置ipv4/ipv6，有告警信息：random: 7 urandom warning(s) missed due to ratelimiting | 吴鹏 | 已验收 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4JVIE
openEuler-20.03-LTS-SP3-round-1 | [20.03 SP3][iSulad] isulad -h命令执行失败 | gaohuatao | 已验收 | sig/iSulad | https://gitee.com/open_euler/dashboard?issue_id=I4JYR6
openEuler-20.03-LTS-SP3-round-1 | [20.03-LTS-SP3]arm上fastdfs包下fdfs_storaged /etc/fdfs/storage.conf start启动失败 |  | 已验收 | sig/Storage | https://gitee.com/open_euler/dashboard?issue_id=I4JZYD
openEuler-20.03-LTS-SP3-round-1 | 【SP3_虚拟镜像arm/x86】qcow2镜像安装系统后，向外部主机scp文件提示：-gt需要一元表达式 | yanan-rock | 已验收 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4K0GO
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86】ldirectord服务启动后有错误Failed to parse PID from file /run/ldirectord.ldirectord.pid | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K0J8
openEuler-20.03-LTS-SP3-round-1 | [20.03 SP3][iSulad] 转测Repo源里的iSulad版本和lcr不匹配，无法启动容器 | small_leek | 已验收 | sig/iSulad | https://gitee.com/open_euler/dashboard?issue_id=I4K0O9
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】rrdcached.socket服务stop之后未删除/tmp/rrdcached.sock文件 | small_leek | 已验收 | sig/Application | https://gitee.com/open_euler/dashboard?issue_id=I4K0Z9
openEuler-20.03-LTS-SP3-round-1 | 【LTS-SP3-RC1】【arm/x86】用memcached+sasl的方式给memcached增加认证，客户端访问失败 | 张瑞方 | 已验收 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4K1H8
openEuler-20.03-LTS-SP3-round-1 | 【SP3-arm/x86】安装iavf有错误信息 | yanan-rock | 已验收 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4K257
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【x86 物理机】虚拟化安装不勾选插件，组raid盘安装系统，报错：Failed to get current device name and index | L.X. | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K267
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm 物理机】net镜像虚拟化安装（选择全部插件），安装好物理机后组raid盘安装虚拟机，虚拟机messages有GPT报错 | 吴鹏 | 已验收 | sig/Kernel | https://gitee.com/open_euler/dashboard?issue_id=I4K2NC
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【x86 物理机】使用net镜像配置anaconda-ks.cfg进行半自动化安装，日志中有 | 杨铭台 | 已验收 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4K34Z
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】perl-Crypt-OpenSSL-Random源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K36H
openEuler-20.03-LTS-SP3-round-1 | 【SP3】卸载abrt-addon-ccpp有错误信息 | small_leek | 已验收 | sig/Application | https://gitee.com/open_euler/dashboard?issue_id=I4K36R
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】openal-soft源码包本地自编译失败 | small_leek | 已验收 | sig/Application | https://gitee.com/open_euler/dashboard?issue_id=I4K38E
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】libffado源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K39F
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86】nfs-blkmap服务停止状态failed.【arm】nfs-blkmap服务启动后状态failed | Markeryang | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K3EI
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】hibernate-validator 源码包本地自编译失败 | small_leek | 已验收 | sig/sig-Java | https://gitee.com/open_euler/dashboard?issue_id=I4K44V
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】mysql5 源码包本地自编译失败 | small_leek | 已验收 | sig/DB | https://gitee.com/open_euler/dashboard?issue_id=I4K46G
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】infinispan源码包本地自编译失败 | small_leek | 已验收 | sig/sig-Java | https://gitee.com/open_euler/dashboard?issue_id=I4K47B
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】python-urwid源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K4LB
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】hivex源码包本地自编译失败 | small_leek | 已验收 | sig/System-tool | https://gitee.com/open_euler/dashboard?issue_id=I4K4M0
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】python-execnet源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K4M3
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】initial-setup.service启动失败 | small_leek | 已验收 | sig/System-tool | https://gitee.com/open_euler/dashboard?issue_id=I4K6ZX
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】rhsm.service启动失败，rhsm-facts.service启动之后日志中报错：cannot watch /etc/rhsm/syspurpose | small_leek | 已验收 | sig/sig-recycle | https://gitee.com/open_euler/dashboard?issue_id=I4K7KS
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】jersey源码包本地自编译失败 | small_leek | 已验收 | sig/sig-Java | https://gitee.com/open_euler/dashboard?issue_id=I4K7LV
openEuler-20.03-LTS-SP3-round-1 | [20.03-LTS-SP3-round-1]arm/x86上sos包下命令行执行报错 | 桐小哥 | 已验收 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4K8JU
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】flink源码包本地自编译失败 | small_leek | 已验收 | sig/sig-ai-bigdata | https://gitee.com/open_euler/dashboard?issue_id=I4K97V
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【arm/x86】openvswitch-ipsec.service启动失败；ovn-controller-vtep.service停止有错误日志ovn-ctl[12958]: [FAILED] | small_leek | 已验收 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4KD51
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【x86/arm】perl-Net-DNS源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4KF89
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】obsapisetup服务启动失败 | small_leek | 已验收 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4KFG6
openEuler-20.03-LTS-SP3-round-1 | 【20.03-LTS-SP3】【arm/x86】edac.service stop的命令使用方式错误 | panxh_purple | 已验收 | sig/sig-recycle | https://gitee.com/open_euler/dashboard?issue_id=I4KFOU
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS SP3】【arm/x86】hbase-master.service服务启动之后没多久状态变为inactive | small_leek | 已验收 | sig/sig-ai-bigdata | https://gitee.com/open_euler/dashboard?issue_id=I4KIA8
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【20.03 SP1】【arm 物理机】进行全量安装或scp，有报错：/etc/profile.d/system-info.sh: 第 17 行：[: -gt：需要一元表达式 | small_leek | 已验收 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4KJFO
openEuler-20.03-LTS-SP3-round-1 | 【libdnf-arm/x86】降级fuse包出现校验报错 | t.feng | 已验收 | sig/sig-OS-Builder | https://gitee.com/open_euler/dashboard?issue_id=I4KKHH
openEuler-20.03-LTS-SP3-round-1 | 【plugin selinux-arm/x86】卸载selinux-policy包出现报错：plugin selinux：hook fsm_file_prepare failed | 卢华歆 | 已验收 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4KQOC
openEuler-20.03-LTS-SP3-round-2 | 【20.03 SP3】ibus从SP1向SP3升级异常 | zhanzhimin | 已验收 | sig/Desktop | https://gitee.com/open_euler/dashboard?issue_id=I4KWWM
openEuler-20.03-LTS-SP3-round-2 | 【iSulad-arm/x86】iSulad从SP2升级到SP3报错 | gaohuatao | 已验收 | sig/iSulad | https://gitee.com/open_euler/dashboard?issue_id=I4L3KW
openEuler-20.03-LTS-SP3-round-2 | [20.03-LTS-SP3][arm物理机]安装最小化加标准插件，message日志报错：/usr/bin/ndctl: No such file or directory | Markeryang | 已验收 | sig/Storage | https://gitee.com/open_euler/dashboard?issue_id=I4L40H
openEuler-20.03-LTS-SP3-round-2 | 【20.03-LTS-SP3】【x86/arm】jffi源码包本地自编译失败 | small_leek | 已验收 | sig/dev-utils | https://gitee.com/open_euler/dashboard?issue_id=I4L7H0
openEuler-20.03-LTS-SP3-round-2 | 【20.03 LTS SP3】【arm/x86】obsnotifyforward.service服务stop失败 | small_leek | 已验收 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4LCPM
openEuler-20.03-LTS-SP3-round-2 | 【20.03-LTS-SP3】【x86/arm】python-pyasn1-modules源码包本地自编译失败 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4LGFY
openEuler-20.03-LTS-SP3-round-2 | [20.03-LTS-SP3-round-2]x86上执行keyring --list-backend命令 python-SecretStorage包下文件告警 | small_leek | 已验收 |  | https://gitee.com/open_euler/dashboard?issue_id=I4LGLK
openEuler-20.03-LTS-SP3-round-2 | 【20.03-LTS-SP3】【x86/arm】nbdkit源码包本地自编译失败 | small_leek | 已验收 | sig/Others | https://gitee.com/open_euler/dashboard?issue_id=I4LINP
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm/x86 物理机】选择中文安装未完全生效，有一部分英文一部分中文的情况 | zhanzhimin | 已挂起 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4JWN5
openEuler-20.03-LTS-SP3-round-2 | 【openEuler 20.03 SP3 Test round 2 】【x86/arm】【日历】节日信息显示异常 | 魏东 | 已挂起 | sig/sig-DDE | https://gitee.com/open_euler/dashboard?issue_id=I4LFHI
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【arm 物理机】net镜像虚拟化安装（选择全部插件），安装好物理机后组raid盘安装虚拟机，虚拟机messages有systemd-udevd报错 | 杨铭台 | 已取消 | sig/Base-service | https://gitee.com/open_euler/dashboard?issue_id=I4K2UJ
openEuler-20.03-LTS-SP3-round-1 | 【20.03 LTS-SP3版本】【x86/arm】ipmidetectd.service执行stop操作之后状态为failed | small_leek | 已取消 |  | https://gitee.com/open_euler/dashboard?issue_id=I4K34R
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP3】【x86 物理机】从SP3向SP1进行全量降级时，nginx-help有报错 | small_leek | 已取消 | sig/Packaging | https://gitee.com/open_euler/dashboard?issue_id=I4K6FA
openEuler-20.03-LTS-SP3-round-1 | 【20.03 SP1 SP2 SP3】【arm/x86 物理机】挂载本地everything源进行安装 | zhanzhimin | 已取消 | sig/sig-OS-Builder | https://gitee.com/open_euler/dashboard?issue_id=I4KIE1
openEuler-20.03-LTS-SP3-round-2 | [SP3 round2] 修改redis配置文件，appendonly no 修改为appendonly yes，重新启动，redis启动失败 | small_leek | 已取消 | sig/sig-ai-bigdata | https://gitee.com/open_euler/dashboard?issue_id=I4L2LL
openEuler-20.03-LTS-SP3-round-2 | 【20.03 LTS SP3】openhpid服务启动失败 | small_leek | 已取消 | sig/System-tool | https://gitee.com/open_euler/dashboard?issue_id=I4LKPN
openEuler-20.03-LTS-SP3-round-2 | 【20.03 SP3】【arm/x86 物理机/虚拟机】SP3全量降级到SP1过程中，环境无法ssh连接 | zhanzhimin | 已取消 | sig/Desktop | https://gitee.com/open_euler/dashboard?issue_id=I4LNIU
openEuler-20.03-LTS-SP3-round-3 | 【SP3-arm/x86】卸载iproute-help子包不应该卸载主包iproute | 蒋恒 | 已取消 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4MBNZ
openEuler-20.03-LTS-SP3-round-3 | 【SP3-arm/x86】卸载dhcp-help子包不应该卸载主包dhcp | yanan-rock | 已取消 | sig/Networking | https://gitee.com/open_euler/dashboard?issue_id=I4MBR6